## How to read
FAR Systems — Phase 2 delivery and Phase 3 boundary
Live site | https://msosa-frontend-topaz.vercel.app
Figma file | https://www.figma.com/design/9EJvzZvBVdbIk4SmTIsbwV/Far-System%E2%84%A2-UP
How to open a portal | Open /login and use Founder, Consumer, Enterprise, Employee, or Refiner. Those buttons open the portal directly.
Delivered screens | Every row is a screen in this delivery. Open the URL. The named screen is there.
Phase 3 | The same screens, later, with a server. Phase 3 does not add or remove a screen, and it is not a reason to reject a screen that already opens.
Not in this agreement | Paused items. They are not in the delivered screens and they are not Phase 3.
This delivery | Static frontend. Demo data lives in the browser. Nothing is saved on a server, no payment is captured, and no model is called.
Agreement | No new paid work. The $7,000 agreement is unchanged. The remaining Phase 2 payment follows acceptance of the delivered screens.

## Delivered screens
Portal | Figma screen | Live URL | What opens
Landing and account | FAR SYSTEMS Official Homepage | https://msosa-frontend-topaz.vercel.app/ | Marketing home
Landing and account | Welcome back | https://msosa-frontend-topaz.vercel.app/login | Sign in, plus the five portal buttons
Landing and account | Create Account | https://msosa-frontend-topaz.vercel.app/register | Individual or Enterprise registration. `/signup` opens the same screen
Landing and account | Check Your Inbox | https://msosa-frontend-topaz.vercel.app/register | Verification step after the registration form
Landing and account | Check Your Inbox, work email | https://msosa-frontend-topaz.vercel.app/employee/signup | Work email, code, then password
Landing and account | Forgot Password | https://msosa-frontend-topaz.vercel.app/forgot-password | Email, code, then a new password
Consumer | Individual Consumer Dashboard | https://msosa-frontend-topaz.vercel.app/consumer/dashboard | Journey tracker, active reflection, Continue, reports, and quick actions
Consumer | Marketplace | https://msosa-frontend-topaz.vercel.app/consumer/customer-products | Consumer products. A product dashboard opens from a product card
Consumer | Checkout | https://msosa-frontend-topaz.vercel.app/consumer/checkout | Purchase form
Consumer | Checkout complete | https://msosa-frontend-topaz.vercel.app/consumer/checkout/success | Confirmation, Start Reflection, and return to the dashboard
Consumer | Reflection Room™ | https://msosa-frontend-topaz.vercel.app/consumer/reflection-room | Voice or text, English or Español, Music / Vibe, Save & Continue
Consumer | Reports Dashboard | https://msosa-frontend-topaz.vercel.app/consumer/report | Report list
Consumer | Report Details View | https://msosa-frontend-topaz.vercel.app/consumer/report/relationship-v2 | Report, version history, Music / Vibe
Consumer | Continuum | https://msosa-frontend-topaz.vercel.app/consumer/continuum | FRC Continuum
Consumer | Profile | https://msosa-frontend-topaz.vercel.app/consumer/profile | Individual profile
Consumer | Notifications | https://msosa-frontend-topaz.vercel.app/consumer/notifications | Notices, with All, Action Required, Blueprint Updates, Organization, and System
Employee | Employee Dashboard | https://msosa-frontend-topaz.vercel.app/employee/dashboard | Sarah Johnson, ABC Healthcare, assigned blueprint, Continue Reflection
Employee | My Blueprint | https://msosa-frontend-topaz.vercel.app/employee/customer-products | My Blueprints. No purchase price on this list
Employee | Reflection Room™ | https://msosa-frontend-topaz.vercel.app/employee/reflection-room | Same room as the consumer, on the employee path
Employee | Reports Dashboard | https://msosa-frontend-topaz.vercel.app/employee/report | Report list
Employee | Report Details View | https://msosa-frontend-topaz.vercel.app/employee/report/relationship-v2 | Report detail
Employee | Employee - Continuum | https://msosa-frontend-topaz.vercel.app/employee/continuum | Professional Development Continuum
Employee | Employee Profile | https://msosa-frontend-topaz.vercel.app/employee/profile | Profile plus department, employee id, and administrator
Employee | Employee Notifications | https://msosa-frontend-topaz.vercel.app/employee/notifications | Same notice filters as the consumer
Enterprise | Enterprise Dashboard v2 | https://msosa-frontend-topaz.vercel.app/enterprise/dashboard | Organization dashboard
Enterprise | Employee Management List | https://msosa-frontend-topaz.vercel.app/enterprise/employee-management | Employee list. Add and edit stay on this page
Enterprise | Employee Detail Page | https://msosa-frontend-topaz.vercel.app/enterprise/employee-management/EMP-0041 | One employee, including Assign Reflection
Enterprise | Blueprint Management List | https://msosa-frontend-topaz.vercel.app/enterprise/blueprint-management | Enterprise products
Enterprise | Blueprint Detail Page | https://msosa-frontend-topaz.vercel.app/enterprise/blueprint-management/bp-leadership | One product, including preview
Enterprise | Invitation Management List | https://msosa-frontend-topaz.vercel.app/enterprise/invitation-management | Invitations. Create invitation stays on this page
Enterprise | Invitation Detail Page | https://msosa-frontend-topaz.vercel.app/enterprise/invitation-management/EMP-0041 | One invitation, secure link, resend, cancel
Enterprise | Participation Monitoring - Overview | https://msosa-frontend-topaz.vercel.app/enterprise/participation-monitoring | Participation list
Enterprise | Participation Monitoring - Employee Detail | https://msosa-frontend-topaz.vercel.app/enterprise/participation-monitoring/EMP-001 | One person's stage and timeline
Enterprise | Reports Center List Page | https://msosa-frontend-topaz.vercel.app/enterprise/reports | Organization reports
Enterprise | Report Detail Viewer Page | https://msosa-frontend-topaz.vercel.app/enterprise/reports/RPT-2026-0041 | One organization report
Enterprise | QCV™ Dashboard | https://msosa-frontend-topaz.vercel.app/enterprise/qcv | QCV overview and comparison
Enterprise | Notification Center List | https://msosa-frontend-topaz.vercel.app/enterprise/notifications | Organization notices
Enterprise | Billing & Subscription Overview | https://msosa-frontend-topaz.vercel.app/enterprise/billing | Plan, usage, and invoices
Enterprise | Billing History & Invoices | https://msosa-frontend-topaz.vercel.app/enterprise/billing/history | Invoice history
Enterprise | Profile Management | https://msosa-frontend-topaz.vercel.app/enterprise/profile | My Profile, Account Settings, Security, and Notification Preferences
Founder | Founder Dashboard - Control Center | https://msosa-frontend-topaz.vercel.app/founder/dashboard | Control Center
Founder | Add New Widget | https://msosa-frontend-topaz.vercel.app/founder/dashboard | Widget library modal on the dashboard
Founder | Edit Widget | https://msosa-frontend-topaz.vercel.app/founder/dashboard | Widget configuration on the dashboard
Founder | Edit Dashboard | https://msosa-frontend-topaz.vercel.app/founder/dashboard | Layout editing on the dashboard
Founder | Create Product™ — Main List | https://msosa-frontend-topaz.vercel.app/founder/create-product | Product list
Founder | Create Product™ wizard | https://msosa-frontend-topaz.vercel.app/founder/create-product | Continue through Basic Info, Reflection, Protocol, Workflow, AI Config, Reports, Dashboard, Permissions, Pricing, and Publish. The Protocol screen is step 3
Founder | Product dashboard builder | https://msosa-frontend-topaz.vercel.app/founder/create-product | Open a product, then its dashboard. Widgets reorder by drag or by Up and Down
Founder | Founder Widget Library Dashboard | https://msosa-frontend-topaz.vercel.app/founder/widget-library | Widget list
Founder | Create New Widget Configuration | https://msosa-frontend-topaz.vercel.app/founder/widget-library/create | New widget form
Founder | Widget Details - Preview & Versions | https://msosa-frontend-topaz.vercel.app/founder/widget-library/WID-FIN-8821 | One widget. Edit is on the same record
Founder | Protocol Library™ | https://msosa-frontend-topaz.vercel.app/founder/protocol-library | Protocol list, create, filter, duplicate, and archive
Founder | Founder User Management Dashboard | https://msosa-frontend-topaz.vercel.app/founder/user-management | Users and roles
Founder | User profile | https://msosa-frontend-topaz.vercel.app/founder/user-management/FAR-US-9921 | One user
Founder | Founder Report Management Dashboard | https://msosa-frontend-topaz.vercel.app/founder/reports | Reports
Founder | Report Templates & Configuration View | https://msosa-frontend-topaz.vercel.app/founder/reports/templates | Report templates
Founder | AI Services Dashboard Overview | https://msosa-frontend-topaz.vercel.app/founder/ai-services | Providers and prompts
Founder | Create New Prompt Page | https://msosa-frontend-topaz.vercel.app/founder/ai-services/create-new-prompt | New prompt
Founder | Link Center Dashboard | https://msosa-frontend-topaz.vercel.app/founder/link-center | Links
Founder | Create New Link Configuration | https://msosa-frontend-topaz.vercel.app/founder/link-center/create | New link
Founder | Founder – Analytics & Insights™ | https://msosa-frontend-topaz.vercel.app/founder/analytics-insights | Analytics
Founder | Founder – Financial Center™ | https://msosa-frontend-topaz.vercel.app/founder/financial-center | Financial overview
Founder | Invoice Listing Dashboard | https://msosa-frontend-topaz.vercel.app/founder/financial-center/invoices | Invoice list
Founder | Invoice detail | https://msosa-frontend-topaz.vercel.app/founder/financial-center/invoices/INV-2024-001 | One invoice
Founder | Founder Control Center profile | https://msosa-frontend-topaz.vercel.app/founder/profile | My Profile, Security, Notification Preferences, Login Sessions, and Activity Log
Founder | Notifications | https://msosa-frontend-topaz.vercel.app/founder/notifications | Founder notices
Refiner | Refiner Dashboard | https://msosa-frontend-topaz.vercel.app/refiner/dashboard | Good morning, Alex Morgan, queue summary, and recent activity. The reviewer name on the profile is Masud J
Refiner | Review Queue | https://msosa-frontend-topaz.vercel.app/refiner/review-queue | Reports needing review
Refiner | Review Queue, open report | https://msosa-frontend-topaz.vercel.app/refiner/review-queue/1041 | One report, section edits, notes, and approve
Refiner | Review History | https://msosa-frontend-topaz.vercel.app/refiner/review-history | Completed reviews
Refiner | Profile & Settings | https://msosa-frontend-topaz.vercel.app/refiner/profile-settings | Profile, security, and notification preferences

## Phase 3
Phase 3 keeps the same URLs. A server stores the result. Until then, the buttons run on demo data in this browser.
Item | What this delivery does | What Phase 3 adds
Account session | Sign in, register, employee signup, and forgot password accept the form and open a portal. Any complete code works. No email is sent. | A real session, a code sent by email, and each portal limited to its own role.
Continue | The stage stays in this browser: Reflection Room, then the product dashboard, then the report. | The same stage is stored on the server and survives another device or a cleared browser.
Reflection answers | Voice and text stay in the browser. | Audio and text are stored against the product the person continued, and that product dashboard shows them.
Journey tracker | The six circles show a fixed demo stage for the selected product. | The circles move from that person's real assignment.
Report opened by Continue | The report stop opens `relationship-v2`. | Continue opens the report for that assignment.
Widgets | Widgets show sample data. | Widgets show that product's live data.
Permissions | Permission flags can be set in Create Product. The portals do not enforce them. | An enterprise user does not see an employee's private reflection text unless that product allows it.
Refiner approval | Approve confirms on the refiner screen. | Approval publishes the report to the member.
PDF | Export and download controls confirm the action. They do not create a file. | A real PDF is generated and delivered.
Protocols | The wizard and Protocol Library can select and edit a protocol in the browser. | Two protocols route to live data on the same architecture.
Enterprise records | Add, assign, invite, purchase, and invoice confirm on the page. A refresh restores the demo. | Employees, assignments, invitations, participation, purchases, and invoices persist.
Employee signup | A work email and any code open the employee dashboard. | The signup requires the invitation email and token sent by the organization.
Founder records | Publish, widgets, protocols, users, prompts, and links last until refresh. | Those records are stored on the server.
Payment | Checkout opens the success page. No charge is made. | Checkout takes payment and grants access. Enterprise billing is a real subscription.
Notifications | Each portal has its own notice list in the page. | Notices are loaded for the signed-in account.
Illumination processing | The processing step is a demo state. No model is called. | The server processes the submitted reflection. The AI choices in Create Product connect to that processing.

## Not in this agreement
These were paused. They are not part of the delivered screens, and they are not Phase 3.
Item | Status
Resize widgets | Outside the agreement
Copy a layout without customer data | Outside the agreement
Tables, schedules, announcements, and awards widgets | Outside the agreement
Custom appearance from reference images | Outside the agreement
AI creating or changing layouts inside Create a Product | Outside the agreement
Image plus instructions, preview, and conversational revisions | Outside the agreement
Save, approve, and restore dashboard templates as a library | Outside the agreement